## Time plan
SF IT2 Test Plan | August | [19 empty] | September | [19 empty] | October
| Week 32 |  |  |  |  | Week 33 |  |  |  |  | Week 34 |  |  |  |  | Week 35 |  |  |  |  | Week 36 |  |  |  |  | Week 37 |  |  |  |  | Week 38 |  |  |  |  | Week 39 |  |  |  |  | Week 40
Milestone | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5
Wave B Test team
Technical Teams
Process Team
Vattenfall onsite
Vattenfal remote
Accenture Preparation
IT3 testing status meetings
IT2 WB configration Sign off
IT3 testing week
@Hamburg
IT3 Kick off
IT3
Ws calls
IT3
WS calls
IT3 - 80% req. provided
@Berlin/Hamburg
IT3
Workshop
IT3 WB Sign off
IT3
Pre-alignment call
IT3 Dress Rehearsal
IT3 WB review and Sign off
Final IT3 TS
Test Script creation support
Dummy Data hierarchy setup
IT3 test
follow up calls
IT3
Sign-off
IT2
Sign-off
IT2 SF test follow up call
IT3 configuration
IT3 test week pre-alignment
IT3 testing status meetings
IT3 testing status meetings
IT3 WB sent to review
Wave B - IT2
Pre-alignment call
Test Scripts IT2
Wave B IT2
Sign-off
LM,RM,SM
Wave B IT2
Sign-off
PM
IT2
Kick-off meeting LM,RM,SM
Data requ. & Data creation
Follow-up calls and retesting LM,SM and RM
Workshop: RM
Workshop: LM
WSP: PM
WSP: SM
Dress Rehearsal
SM, LM, RM
Load the Test Scripts on SP
Dress Rehearsal
PM
Follow-up calls and retesting PM
Wave B IT2 test:
Performance (Stocklom)
IT2
Kick-off meeting PM
Wave B IT2 test:
Recruiting (Stocklom)
Wave B IT2 test:
Learning: (Amsterdam)
Wave B IT2 test:
Succession (Stocklom)

## Wave A - IT 4 Activity plan
IT4 Activity plan
Activity | Comment | Responsible | Status | Deadline
Test data creation
Employee Central | Reuse from IT 3 - See Excel with test employee data on Foxtrot SharePoint. TBD if some employees need to be manually fixed so that Org chart and Position charts are aligned. Most Open positions are in wrong LE, TBD if these need to be manually fixed |  | Not started
Onboarding | Some open positions need to be created |  | Not started
Comp and Variable pay | A few users for Compensation & VP with leave of absence data (after configuration in EC) |  | Not started
Benefits | Reuse from IT 3 |  | Finished
RBP | Reuse. Possible to use Antoine Friedman, Karson Hays or with Lexie Ray. These employees had data enriched by Sebastian/Roger for IT3 tests | Sebastian/Roger | Finished
Test script creation/update
Overall scope of IT 4 test scripts to be decided and aligned | Proposal need to be created and aligned with SF Process leads and with Vattenfall | Sahana | Not started
Employee Central: Test scripts and Defect | New test scripts needed or updates of old test scripts? Check after WS if Open item decisions from IT4 Workshops can create need for new TS. List of defects for re-test | Andres | Not started
Onboarding | Change of test scripts to align with Recruitment. List of Open defects and new translations | Helle | Not started
Comp and Variable pay | Create Additional test script needed for both ASR and STI for testing market allowance and Leave of absence. List of defects for re-test | Diogo | Not started
Benefits | Already decided that no new Benefits test scripts are needed. List of defects for re-test | Olivier | Not started
RBP | Already decided that no new RBP test scripts are needed. List of defects for re-test | Sebastian | Not started
Language re-test defects TBD | Many language defects were fixed using Bernhard Language Excel used in IT3 tests. TBD the method to re-test this and the scope (for example if any translations of SF standard language is to be included) | Bernhard | Not started
Test Management prep
Request IT4 Final Participants list from Vattenfall | Request list of testers from VF (Satyabrata Patra) | Sahana/Carmen/Satyabrata | Not started | Request to VF May 30th? VF should provide this June 4th
Test exit criteria IT4 TBD with Vattenfall | Decide on general exit criteria for Wave A IT4 sign off. How many test scripts tested (Passed or Failed). How many % Passed/Passed with minor defects test scripts are needed? How many Critical or High Defect are allowed. Check exit criteria used for IT3 | Sahana/Carmen | Not started | May 31st
Create: IT4 Test week schedule | See Excel template used in Wave A. Plan onsite sessions and VF participants/testers + developers Plan skype follow up calls | Sahana/Carmen | Not started | June 4th
IT4 send out Skype follow up calls. | Plan when calls are needed (daily?). VF.Foxtrot (PMO/Suzy) to send out mail calendar invititation to VF participants | Sahana/Carmen and PMO | Not started | June 4th
Accenture internal pre-alignment call with SF leads and Suzy/Varun | If needed? | Sahana/Carmen/Suzy/Varun | Not started | June 7th?
Plan VF testers to test the defects and test scripts to re-test | Based on list of VF testers and based on scope of test scripts and defects | Sahana/Carmen | Not started | June 7th?
Create Kick-off PPT | Re-use some slides from SF IT 3 Kick off PPT | Sahana/Carmen | Not started | June 8th
Test information mail to testers | Send info mail with links to Foxtrot SP, PPT, list of login users (check with EC team that we can use same users and passwords as in IT3). | Sahana/Carmen | Not started | June 8th
Defect master and Test script execution tracker | Check that they are updated and we have correct versions. Check routine to update the Grandmaster excels | Carmen | Not started | June 8th
Test Management during IT4 test week
IT4 Kick-off call | Skype call on 8th of June | Sahana/Carmen | Not started | June 8th
Hold Test sessions, possible daily status calls and defect/re-test follow up-calls | General activity each day: Based on test schedule and Calendar invitations | Sahana/Carmen | Not started | June 8th until June 15th
Send out daily status mails during test weeks | At end of each day with statistics | Carmen? | Not started | June 8th until June 15th
IT 4 Sign-off | Receive sign-off via VF (Satyabrata) | Sahana/Carmen/Satyabrata | Not started | June 15th
Create/send out SF IT4 Test closure report | TBD if needed and who creates this (see example from Wave A - SF IT 2 tests) | ? | Not started | June 15th
Ref below from IT3
Phase 1: IT3 upstart
IT2 follow-up call |  | Test/ tech teams | Finished | w12
Fixing IT2 Open Items |  | Tech teams | In progress | w14
IT2 Sign-off |  | Vattenfall | Finished | 23/3 w12
IT3 kick-off |  | Tech/ Process teams | Finished | 21/3 w12
IT3 high level plan |  | Test team | Finished | w12
Vattenfall requirements for IT3 testing |  | Vattenfall/ Satya pratya | Finished | 29/3 w13
Phase 2: IT3 test Preparation week 14-16
Final Participants list from Vattenfall | Satya to deliver Thursday April 5th | Vattenfall/ Process Team | In progress | 5/4 w.14
Update Master Execution Tracker | Test team updates daily. Must be ready for delivery to VF April 13. | Test team | In progress | w14-15-16
Testing check-in calls with tech teams | Meetings setup and to be conducted through w13-15. Need to setup meetings for EC, RBP, OOB w15 | Test team | In progress | w13-15
Test Script creation IT3 | Challenge: EC how to incorporate IT3 alongside workshop w15 | Test team | In progress | w14+15+16
IT3 test data set | Mock2 data to be used for EC, RBP, OOB. IT2 test data to be used for Comp, var. Pay, PCP, Ben | Tech teams | In progress | w14+15
IT3 Data loads | Malene to load add. Data for Benefits | Test team | In progress | w16
IT3 workshop follow up calls | EC + benefits onsite workshop w15 | Tech/ process team | In progress | w13+14+15
IT3 configuration |  | Tech team | Not started | w16
Prepare Pre-alignment call ppt. 1xVF + 1xInternal | Malene have contacted Suzy to setup internal alignment call. Need to find a date | Test team | In progress | 13/4 w15
IT3 WB Requirements |  | Vattenfall | Not started | w14+15
Move mock 2 data to dev. Environment | Dependent on Mock 2 data to be ready in quality environment 13/4. depends on Mock2 decision? | Test team | Not started | 16/4 w16
Finalizing Test Scripts | VF Requirement: Send Master Execution Tracker to VF for review the 20th? Ask Satya. Send test scripts two days before test week. | Test team | Not started | 20/4 w16?
Link TS and Mock 2 data to packages |  | Test team | Not started | 20/4 w16?
Phase 3: Dress rehearsal phase
IT3 Test week schedule |  | Test team | Not started | w17
IT3 testing Prealignment call w. Vattenfall |  | Test team | Not started | w17
IT3 WB review |  | Vattenfall | Not started | w16
IT3 WB sign off |  | Vattenfall | Not started | 20/4 w16?
IT3 Dress rehearsal |  | Test team | Not started | w17
Division of testers/rooms/ACN resources |  | Test/Tech/Process team | Not started | 27/4 w17
Defect tracker |  | Roger | Not started | 27/4 w17
IT3 test week internal pre-alignment |  | Test team | Not started | w17
Kick off presentation |  | Test team | Not started | w17
Phase 4: IT3 testing week
Kick off |  | Test team | Not started | 30/4 w18
Testing |  | All | Not started | w18+19?
Defect tracker daily update |  | Roger | Not started | w18
Status meetings |  | Test team | Not started | w1+19?
IT3 testing follow up calls |  | Test/ tech teams | Not started | w19+20?
IT3 sign off |  | Vattenfall | Not started | w19 or20?

## Wave B - IT1 Activity plan
IT4 Activity plan
Activity | Comment | Responsible | Status | Deadline
Test data creation
Excel template on SF data requirements to send out to SF process leads | Send out to SF process leads to align on requirements on the test data needed. Sahana to set up meeting with Wave B leads. See Excel template for employee data (sent by Roger) | Sahana/Carmen | Not started | May 29?
TBD if EC test employee hierarchy can be used as baseline | Check with EC team + Roger. Based on what requirements that SF leads have | EC team/Roger
Create Recruitment data |  | ? | Not started
Create Learning data |  | ? | Not started
Create Succession Management data |  | ? | Not started
Create Performance Management data |  | ? | Not started
Test script creation
Create Recruitment test scripts | SF developers to create test script. Based on IT1 Workshops. Possibly some Accenture HV test scripts can be used as reference | ? | Not started | June 1st
Create Learning test scripts | SF developers to create test script. Based on IT1 Workshops. Possibly some Accenture HV test scripts can be used as reference | ? | Not started | June 1st
Create Succession Management test scripts | SF developers to create test script. Based on IT1 Workshops. Possibly some Accenture HV test scripts can be used as reference | ? | Not started | June 1st
Create Performance Management test scripts | SF developers to create test script. Based on IT1 Workshops. Possibly some Accenture HV test scripts can be used as reference | ? | Not started | June 1st
Overall scope of Wave B test scripts to be decided and aligned | The list of test scripts to be collected in Wave B master test script execution tracker. The scope need to be aligned both with Accenture SF process leads and with VF (Satyabrata). Satyabrata will probably send the list to relevant VF people for alignment of scope with them | Sahana/Carmen | Not started | Send list to VF June 4th latest. Present on pre-alignment call?
Create: Master test script execution tracker | With list + scope of all test scripts | Sahana/Carmen/Roger | Not started
Test Management prep
SF Test team alignment on method for update of Defect master + Test script execution tracker | SF Test team to align on method for update of Defect master + Test script execution tracker. Check if we need decentralized trackers or only one each. Align on statistics to use. | Sahana/Carmen/Roger | Not started | May 30th
Request Final Participants list from Vattenfall | Request list of testers from VF (Satyabrata Patra) | Sahana/Carmen/Satyabrata | Not started | Request to VF May 30th? VF should provide this June 4th
Test exit criteria TBD with Vattenfall | Decide on general exit criteria for Wave B IT1 sign off. How many test scripts tested (Passed or Failed). How many % Passed/Passed with minor defects test scripts are needed? How many Critical or High Defect are allowed. Check exit criteria used for Wave A | Sahana/Carmen | Not started | June 4th
Create: IT1 Test week schedule | See Excel template used in Wave A. Plan onsite sessions and VF participants/testers + developers Plan skype follow up calls | Sahana/Carmen | Not started | June 4th
IT1 Send out mail invitations for onsite sessions and Skype follow up calls. | Use the Test schedule as above + VF participants list. VF.Foxtrot (PMO/Suzy) to send out mail calendar invititation | Sahana/Carmen and PMO | Not started | June 4th
Accenture internal pre-alignment call with SF leads and Suzy/Varun | If needed? | Sahana/Carmen/Suzy/Varun | Not started | June 4th
Dress rehearsal test | (Probably) BPO to test the test scripts and check that processes in Test scripts are aligned with BPO process maps. Test together with SF developers (the developers who created the test scripts) | BPO/SF teams | Not started | June 5th - June 8th
Create: Kick-off PPT/Pre-alignment PPT | Re-use some slides from Wave A Kick off PPT | Sahana/Carmen | Not started | June 5th
Wave B : Pre-alignment call - June 5th | Present for VF via Skype: IT1 Test week schedule (see above) Overall scope of Wave B test scripts (possibly in the Master test script execution tracker) Pre-alignment PPT or early version of Kick off PPT | Sahana/Carmen | Not started | June 5th
Plan VF testers connected to test the Test scripts | Use the Wave B version of Master test script execution tracker. Based on list of VF testers and based on scope of test scripts | Sahana/Carmen | Not started | June 8th
Create login users in SF | Use VF participants list to create technical login users with proxy auth. Please note that it should be in Wave B instance | EC team | Not started | June 8th
Test information mail to testers | Send info mail (on day of tests) with links to Foxtrot SP, PPT, list of login users (check if same users and pw as in IT3). | Sahana/Carmen | Not started | June 11th
Defect master | Create Empty Excel Defect master. | Sahana/Carmen | Not started | June 11th
Test Management during Wave B test weeks
Wave B IT1 Kick-off meeting | First day of testing. Onsite meeting on 11th of June | Sahana/Carmen | Not started | June 11th
Wave B IT1 Kick-off meeting Perf Management | First day of testing for Performance Man. Onsite meeting on 18th of June | Sahana/Carmen | Not started | June 18th
Hold Test sessions, possible daily status calls and defect/re-test follow up-calls | General activity each day: Based on IT1 test schedule and Calendar invitations | Sahana/Carmen | Not started | June 11th until June 29th
Send out daily status mails during test weeks | At end of each day with statistics | Carmen? | Not started | June 11th until June 29th
Wave B IT 1 Sign-off | Receive sign-off via VF (Satyabrata) | Sahana/Carmen/Satyabrata | Not started | June 25th
Wave B IT 1 Sign-off Perf Management | Receive sign-off via VF (Satyabrata) | Sahana/Carmen/Satyabrata | Not started | July 2nd
Send out SF Wave B, IT1 Test closure report | TBD who creates this (see example from Wave A - SF IT 2 tests) |  | Not started | July 2nd

## Scope and decisions
Scopes and decisions
Issue | Comment | Responsible | Status | Deadline
Iteration 4 testing is mostly testing open defects from iteration 3 with the exception of –
1. Onboarding – Changes to translations, changes for alignment with recruitment iteration 1 requirements.
2. Compensation & Variable Pay – Additional test script needed for both ASR and STI for testing market allowance and Leave of absence.
3. EC and Benefits can reuse the test scripts but for EC, Andres will reconfirm after the workshop.
4. RBP test scripts will not be created for iteration 4 but will be created for UAT and automation tool used for testing. Only retesting of open defects is in scope here. If anything changes, please keep me informed.
Test Script - Test script approach for all is to reuse the test scripts, modify where necessary and provide a clear list of scripts to be run and defects to be retested for iteration 4.
Test Data – Testing team will support with data creation. Please provide your requirements soon after the workshops on Monday. And once created, this needs to be included within the test scripts. There will be no dress rehearsal testing for this iteration.
Test Data needed –
1. A few users for Compensation & VP with leave of absence data (after configuration in EC)
2. A few positions for Onboarding
3. Reuse test data for EC and Benefits.
Timeline -
1. Kick off Call and Day 1 testing begins on June 8th. This is planned to be virtual.
2. Testing continues till 14th with signoff expected on 15th June.
3. As per the plan it looks like the location from 11th to 14th June is BER/AMS. This coincides with iteration 1 testing for wave B. Varun to confirm if the testing will be virtual or at these locations.
4. Testing team will be one person each in Stockholm, Berlin and Amsterdam supporting wave B.
5. Onboarding testers may have a challenge testing wave A and B at the same time.
Tracking and Defect Management –
1. We continue to use the trackers from iteration 3.
Instances –
1. Wave B will test in a different instance than wave A. We will get the new instance which is a copy soon. All iteration 4 changes have to be made in both instances and all defects should be fixed in both instances. Please align with Varun on this if you see any concerns.

## Dates from WS master
June 5 | SF IT1 - Unit Test Pre-Alignment
June 11 | SF IT1 - Learning Unit Test - Day 1
SF IT1 - Succession Management Unit Test - Day 2
SF IT1 - Recruitment Unit Test - Day 1
Migration - SF Mock 3 - Test Kick Off

## IT 4 lessons learned
Area | Issue | Description/Mitigation | Other notes
Test data RBP | Not enough data on employees | Enrich employee data on employees to be used for IT 4. For example Use Antoine Friedman, Karson Hays or Lexie Ray.
Test data EC | Org hierarchy and Position hierarchy not in synch | Create new employee data hierarchy
Test data EC | Open positions not correct | Create new Open pos
Planning |  | Important with planning of milestones of when Open items and scope of IT4 => to give time for creating new test script versions. Open items, Language, new developments, Autodelegate
scope of IT4 |  | Clear scope need to be decided What to test. How many WF to re-test from IT3
stats | Test script execution stats | Use stats created by Mark or Pivot stats as created by Malene/Christine
1. How do we use the grandmaster file to get the statistics. How do we maintain the grandmaster file. What information is needed by Vf daily, is this format frozen?
| Master test script execution tracker | Option 1: Proposal to use only one centralized Master test script execution tracker. And ask testers to update this. The testers do not need to update this so much => It should be OK to use only one
| Master test script execution tracker | Option 2: Continue with decentralized Master test script execution tracker
| Defect master | Option 1: Continue to use decentralized defect master
| Defect master | Option 2: Use only on master Defect master. Maybe possible if not so many testers in IT4
| Defect master | Option 3: Use the SP list item functionality created by Mark
| 2. Process used in iteration 2 and 3 for coordination with the different streams, approach and plan used. Roger has provided us with some input today and it would be good to get any input you have Malene. | See slide 8 in Kick off PPT
3. Outstanding items for iteration 3, how and when should I take over? What exactly is needed this week?

## IT3 Activity Plan
IT3 Activity plan
Activity | Responsible | Status | Comment | Location Specification | Deadline
Phase 1: IT3 upstart
IT2 follow-up call | Test/ tech teams | Finished |  | Virtual | w12
Fixing IT2 Open Items | Tech teams | In progress |  |  | w14
IT2 Sign-off | Vattenfall | Finished |  | E-mail | 23/3 w12
IT3 kick-off | Tech/ Process teams | Finished |  | Virtual | 21/3 w12
IT3 high level plan | Test team | Finished |  |  | w12
Vattenfall requirements for IT3 testing | Vattenfall/ Satya pratya | Finished |  |  | 29/3 w13
Phase 2: IT3 test Preparation week 14-16
Final Participants list from Vattenfall | Vattenfall/ Process Team | In progress | Satya to deliver Thursday April 5th |  | 5/4 w.14
Update Master Execution Tracker | Test team | In progress | Test team updates daily. Must be ready for delivery to VF April 13. |  | w14-15-16
Onboard Prague + Bucharest resources | Test team | Finished | Malene in Prague, Carl in Bucharest w14. |  | w14
Test User creation | Malene | In progress | Do they use their user from IT2? |  | w15
Testing check-in calls with tech teams | Test team | In progress | Meetings setup and to be conducted through w13-15. Need to setup meetings for EC, RBP, OOB w15 |  | w13-15
Test Script creation IT3 | Test team | In progress | Challenge: EC how to incorporate IT3 alongside workshop w15 |  | w14+15+16
IT3 test data set | Tech teams | In progress | Mock2 data to be used for EC, RBP, OOB. IT2 test data to be used for Comp, var. Pay, PCP, Ben |  | w14+15
IT3 Data loads | Test team | In progress | Malene to load add. Data for Benefits |  | w16
IT3 workshop follow up calls | Tech/ process team | In progress | EC + benefits onsite workshop w15 | Virtual | w13+14+15
IT3 configuration | Tech team | Not started |  |  | w16
Prepare Pre-alignment call ppt. 1xVF + 1xInternal | Test team | In progress | Malene have contacted Suzy to setup internal alignment call. Need to find a date |  | 13/4 w15
IT3 WB Requirements | Vattenfall | Not started |  | E-mail | w14+15
Move mock 2 data to dev. Environment | Test team | Not started | Dependent on Mock 2 data to be ready in quality environment 13/4. depends on Mock2 decision? |  | 16/4 w16
Finalizing Test Scripts | Test team | Not started | VF Requirement: Send Master Execution Tracker to VF for review the 20th? Ask Satya. Send test scripts two days before test week. |  | 20/4 w16?
Link TS and Mock 2 data to packages | Test team | Not started |  |  | 20/4 w16?
Phase 3: Dress rehearsal phase
IT3 Test week schedule | Test team | Not started |  |  | w17
IT3 testing Prealignment call w. Vattenfall | Test team | Not started |  | Virtual | w17
IT3 WB review | Vattenfall | Not started |  |  | w16
IT3 WB sign off | Vattenfall | Not started |  | E-mail | 20/4 w16?
IT3 Dress rehearsal | Test team | Not started |  | TBD | w17
Division of testers/rooms/ACN resources | Test/Tech/Process team | Not started |  |  | 27/4 w17
Defect tracker | Roger | Not started |  |  | 27/4 w17
IT3 test week internal pre-alignment | Test team | Not started |  | Onsite/Call | w17
Kick off presentation | Test team | Not started |  |  | w17
Phase 4: IT3 testing week
Kick off | Test team | Not started |  | Hamburg | 30/4 w18
Testing | All | Not started |  | Hamburg | w18+19?
Defect tracker daily update | Roger | Not started |  | Hamburg | w18
Status meetings | Test team | Not started |  | Hamburg | w1+19?
IT3 testing follow up calls | Test/ tech teams | Not started |  | Virtual | w19+20?
IT3 sign off | Vattenfall | Not started |  | E-mail | w19 or20?

## Requirements (to be updated)
IT3 Requirements 26/3 2018
To do | Deadline | Responsible | status
IT3 testing requirements (participants, test scripts to run, defects to focus on)+ final list of participants delivered by Vattenfall | 3/4 2018 | Roger | in progeress
Setup meetings in w14 with functional leads and pre-align on test scripts approach | 26/3 2018 | Malene/Roger | done
Data loads - how do we do it best? | Raise it at Meeting 26/3 2018 |  | In progress. Priority w14
Setup Internal Kick off meeting w. Suzy. Date? | 26/3 2018 | Malene | In progress
Determine Process team resources | 28/3 2018 | Malene | done
Alignment of who is in charge of what during the test week: who book rooms etc.? Suggestion: send out an email with test week info | 6/3 2018 | Malene | In progress. VF PMO Mark. Contact and align
Role scope - responsibilities?

## Notes
Status
In progress
Not started
Finished

## IT3 Plan
SF IT3 Project Plan | March | [9 empty] | April | [19 empty] | May | [24 empty] | June | [19 empty] | July
| Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Week 21 |  |  |  |  | Week 22 |  |  |  |  | Week 23 |  |  |  |  | Week 24 |  |  |  |  | Week 25 |  |  |  |  | Week 26 |  |  |  |  | Week 27
Milestone | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 2 | 3 | 4 | 5 | 6
Wave A Test team
Wave B Test team
Technical Teams
Process Team
IT3 Upstart
Vattenfall onsite
Vattenfal remote
IT3 testing week
@Hamburg
IT2 SF test follow up call
IT2
Sign-off
Internal
IT3 testing week
@Hamburg
IT3 testing week
@Hamburg
IT3 Kick off
IT3
Ws calls
IT3
WS calls
IT3 Kick off
IT3
follow up calls
IT3
follow up calls
Mock 2 data ready.
IT3 - 80% req. provided
IT3 - 80% req. provided
@Berlin/Hamburg
IT3
Workshop
IT3 WB review and Sign off
IT3 WB Sign off
IT3 WB Sign off
IT3 WB Sign off
IT3
Pre-alignment call
IT3
Pre-alignment call
IT3 Dress Rehearsal
IT3 Dress Rehearsal
IT3 Dress Rehearsal
IT3 WB review and Sign off
IT3 WB review and Sign off
Test Script creation
Final IT3 TS
Test Script creation support
Dummy Data Loads for Comp, Var. Pay, PCP + Ben
Final IT3 TS
Final Test
Data
Dummy Data hierarchy setup
IT3 test
follow up calls
IT3 test
follow up calls
IT3 test
follow up calls
IT3
Sign-off
IT3
Sign-off
IT3
Sign-off
Defect fixing
IT2
Sign-off
IT2 SF test follow up call
IT2 SF test follow up call
IT2
Sign-off
IT3 configuration
IT3 test week pre-alignment
IT3 test week pre-alignment
IT3 test week pre-alignment
IT3 testing status meetings
IT3 testing status meetings
IT3 testing status meetings
Phase 1
Phase 2
Phase 3
Phase 4 - To be confirmed
IT3 Phase
IT3 WB sent to review
IT3 WB sent to review
Mock 2 in dev. env.
Combining Mock2 + TS
@Berlin/Hamburg
IT3
Workshop
@Prague&Bucharest resource onboarding
Master Ex. Tracker to VF
Test scripts to VF
Open items ready
Translations ready
IT4 test + re-test of defects
Wave A - IT4
Kick-off call
Test Script: Update of IT3 test scripts
Workshops IT4
IT4 WB Sign off
IT3 testing week
@Hamburg
IT3 Kick off
IT3
Ws calls
IT3
WS calls
IT3 - 80% req. provided
@Berlin/Hamburg
IT3
Workshop
IT3 WB Sign off
IT3
Pre-alignment call
IT3 Dress Rehearsal
IT3 WB review and Sign off
Final IT3 TS
Test Script creation support
Dummy Data hierarchy setup
IT3 test
follow up calls
IT3
Sign-off
Defect fixing
IT2
Sign-off
IT2 SF test follow up call
IT3 configuration
IT3 test week pre-alignment
IT3 testing status meetings
IT3 testing status meetings
IT3 WB sent to review
Test data updates
Wave B
Pre-alignment call
Wave B test - Onsite
IT4
Sign-off
Workshops Wave B
New test scripts IT1
Test data creation
Dress rehearsal test
Wave B Test: Performance management
Wave B IT1
Sign-off
Wave B IT1
Perf man
Sign-off
PM Dress rehearsal test
Note on BG5: Sveningsson, Roger: Sweden holiday
Note on BS5: Sveningsson, Roger: Sweden holiday