## Checklist
Test Type | Activity Details | Planned | Actual | Responsible | Revised planned date | Comments
Iteration- 4 (Wave A) | Development Readiness | 7th June 2018 |  | ACN
| Test Environment Readiness | 7th June 2018 |  | ACN
| Resources Finalization | 30th May 2018 |  | VF/ACN |  | EC and RBP testers are pending. Rest are in the tab called Testers for wave A iteration 4
| Test approach | 28th May 2018 | 28th May 2018 | ACN |  | Final deck is shared
| Test scripts to be ready | 7th June 2018 |  | ACN
| Test Data to be ready | 7th June 2018 |  | ACN
| Final Scenarios in Master Execution Tracker | 7th June 2018 |  | ACN |  | 6th June is a holiday in Sweden.
| Test script Review | 7th June 2018 |  | VF |  | 6th June is a holiday in Sweden.
| Test Kick Off Call | 8th June 2018 |  | ACN/VF |  | Already Scheduled
| Work book sign off | 5th June 2018 |  | VF
| Test Execution | 8th June - 14th June 2018 |  | VF
| Test Closure report | 15th June 2018 |  | ACN/VF
Test Type | Activity Details
Iteration 1 (Wave B) | Development Readiness | 7th June 2018 |  | ACN
| Test Environment Readiness | 7th June 2018 |  | ACN
| Resources Finalization | 30th May 2018 |  | VF/ACN |  | Testers are already invited and please find the tab testers for wave B iteration 1 for the names. RBP testers need to be estimated.
| Test approach | 28th May 2018 |  | ACN
| Test scripts to be ready | 7th June 2018 |  | ACN |  | 6th June is a holiday in Sweden.
| Test Data to be ready | 7th June 2018 |  | ACN
| Final Scenarios in Master Execution Tracker | 8th June 2018 |  | ACN
| Test script Review | 7th June 2018 |  | VF |  | 6th June is a holiday in Sweden.
| Test Alignment call | 5th June 2018 |  | ACN/VF
| Work book sign off | 4th June 2018 |  | VF
| Test Execution | 11th June - 15th June 2018 18th June to 22nd June |  | VF |  | Performance is in week 25 and all others in week 24
| Test Closure report | 29th June 2018 |  | ACN/VF

## Testers for wave A Iteration 4
|  |  | Dates Allocated | 2018-06-08 | 2018-06-11 | 2018-06-12 | 2018-06-13 | 2018-06-14 | 2018-06-15
|  |  | Original Distribution of Testing | Wave A Test | Wave A Test | Wave A Test | RETEST | RETEST | SIGNOFF | Invites sent?
Compensation and Variable Pay | [11 empty] | Needed for Mock 3 Testing
1 | Anna Heder | SE | 4 hours | 2018-06-11: Wave A Test |  | LOA is ready only on Monday since Comp has dependency with EC, this can be only tested on Monday. | Needed for Wave B IT1 Testing
2 | Jena Hedbeck | SE | 4 hours | 2018-06-11: Wave A Test |  | LOA is ready only on Monday since Comp has dependency with EC, this can be only tested on Monday. | Information Pending
3 | Marcella Schokker | NL | 4 hours | 2018-06-11: Wave A Test; 2018-06-12: RETEST; 2018-06-14: MOCK 3 |  | LOA is ready only on Monday since Comp has dependency with EC, this can be only tested on Monday.
4 | Dirk Kunath | DE | 4 hours | 2018-06-11: Wave A Test; 2018-06-12: RETEST
5 | John Bowling | UK | 4 hours | 2018-06-11: Wave A Test; 2018-06-12: RETEST |  | Replacement Peggy
6 | Laura Schutte | DE | 4 hours | 2018-06-13: MOCK 3; 2018-06-14: MOCK 3; 2018-06-15: MOCK 3 |  | No testing is needed. No open defects for Laura and no changes.
7 | Caroline van Minde |  | 4 hours |  |  | Wave A Test | MOCK 3 | MOCK 3 | MOCK 3 |  | Also needed for RBP. Test and Retest for Wave A needs to be on 13th June.
Benefits
1 | Christian Rehorst | DE | 4 hours | Wave A Test | Wave A Retest |  |  | MOCK 3 | MOCK 3 |  | Olivier to confirm on Monday
2 | Kristina Stelter-Hinkel | DE | 4 hours | Wave A Test | Wave A Retest | MOCK 3 | MOCK 3 |  |  |  | Olivier to confirm on Monday
3 | Ingela TBC | SE | 2 hours | 2018-06-08: Wave A Test
Employee Central and FO
1 | Beate Stoltze | DE |  | Wave A Test | PTO | PTO | PTO | PTO | PTO |  | On leave from 11-Jun onwards. Stefan is perhaps the replacement
2 | David Brink | NL |  | Wave A Test | Wave A Test | Wave A Retest | MOCK 3 | MOCK 3 | MOCK 3 |  | This is ok.
3 | Ingela Månström | SE |  | 2018-06-08: Wave A Test; 2018-06-11: Wave A Test; 2018-06-12: Wave A Retest |  | For Sweden, one more tester is needed.
4 | John Bowling | UK |  | Wave A Test | Wave A Test | Wave A Test | Wave A Retest | Wave A Retest |  |  | Replacement Peggy
5 | Gertjan Meijer | NL |  | Wave A Test | Wave A Test | Wave A Test | Wave A Retest | Wave A Retest
6 | Stefan Delor | DE |  | Wave A Test | Wave A Test | Wave A Test | Wave A Retest | Wave A Retest
7 | Alan God | Glo | [8 empty] | Potential to reassign to RBP | bar: 2018-06-08 to 2018-06-14
RBP
1 | Caroline van Minde | Glo |  | 2018-06-13: MOCK 3; 2018-06-14: MOCK 3; 2018-06-15: MOCK 3 |  | Also needed for Comp. Not needed for EC.
2 | Magdalena Brysiak | Glo |  | 2018-06-11: Wave A Test; 2018-06-12: WAVE B; 2018-06-13: Wave A Retest |  | Wave B Iteration 1 Testing
Onboarding
1 | Camilla Jacobson or Lovisa Strid to test for SE | SE | 8 hours | Wave A Test | Wave A Test | Wave A Test | Wave A Retest | Wave A Retest |  |  | Camilla is testing iteration 1
2 | Karlijn Mares to test NL | NL | 8 hours | Wave A Test | Wave A Test | Wave A Test | Wave A Retest | Wave A Retest
3 | Tatiana Als to test UK | UK | 1 defect - 1 hour | 2018-06-08: Wave A Test; 2018-06-11: Wave A Retest
4 | Michael Brilke or Tatiana Als to test DE | DE | 8 hours | Wave A Test | Wave A Test | Wave A Test | Wave A Retest | Wave A Retest
Wave B
Succession
1 | camilla jacobson |  | Full days in workshop |  |  | WAVE B (half day) | WAVE B | WAVE B | WAVE B (half day)
2 | antje van willigen |  | Full days in workshop |  |  | WAVE B (half day) | WAVE B | WAVE B | WAVE B (half day)
3 | Anja Sergijenko |  | Full days in workshop |  |  | WAVE B (half day) | WAVE B | WAVE B | WAVE B (half day) |  | Not invited
4 | Uta Schellenberger-nicoubin |  | Full days in workshop |  |  | WAVE B (half day) | WAVE B | WAVE B | WAVE B (half day) |  | Not invited
5 | jayesh lindh | [9 empty] | uta.schellenberger-nicoubin@vattenfall.de | bar: 2018-06-11 to 2018-06-15
6 | Malin AlexisNordin | bar: 2018-06-11 to 2018-06-15
Learning
1 | Femke Bartels |  | Full days in workshop |  |  | WAVE B | WAVE B | WAVE B | WAVE B
2 | Annika Borlin |  | Full days in workshop |  |  | WAVE B | WAVE B | WAVE B | WAVE B
3 | Rene Tschierwitz |  | Full days in workshop |  |  | WAVE B | WAVE B | WAVE B | WAVE B
4 | Michael Neukirch |  | Full days in workshop | bar: 2018-06-11 to 2018-06-15
5 | Elisabeth Laitla |  | Full days in workshop |  |  | WAVE B | WAVE B | WAVE B | WAVE B
6 | Rainer Bitschi |  | Full days in workshop |  |  | WAVE B | WAVE B | WAVE B | WAVE B
7 | Antje Van Willigen | bar: 2018-06-11 to 2018-06-15
8 | Alan God | bar: 2018-06-11 to 2018-06-15
9 | Patrick Roscher | bar: 2018-06-11 to 2018-06-15
10 | Dam joost Van | bar: 2018-06-11 to 2018-06-15
Recruiting
1 | angelika Fuechtenhans |  | Full days in workshop |  |  | WAVE B | WAVE B | WAVE B | WAVE B
2 | jasmine vant hul |  | Full days in workshop |  |  | WAVE B | WAVE B | WAVE B | WAVE B
3 | bastiaan moll |  | Full days in workshop |  |  | WAVE B | WAVE B | WAVE B | WAVE B
4 | anna karin claeson |  | Full days in workshop |  |  | WAVE B | WAVE B | WAVE B | WAVE B
5 | jayesh lindh |  | Full days in workshop |  |  | WAVE B | WAVE B | WAVE B | WAVE B
6 | linn ljungman |  | Full days in workshop |  |  | WAVE B | WAVE B | WAVE B | WAVE B
7 | anja sergijenko |  | Full days in workshop |  |  | WAVE B | WAVE B | WAVE B | WAVE B
8 | lorraine melissen |  | Full days in workshop |  |  | WAVE B | WAVE B | WAVE B | WAVE B
9 | pi lindstroem |  | Full days in workshop |  |  | WAVE B | WAVE B | WAVE B | WAVE B
10 | antje van willigen |  | Full days in workshop |  |  | WAVE B | WAVE B | WAVE B | WAVE B
11 | linn rejstrom |  | Full days in workshop |  |  | WAVE B | WAVE B | WAVE B | WAVE B
12 | daniel t nilsson |  | Full days in workshop |  |  | WAVE B | WAVE B | WAVE B | WAVE B
Performance
[6 empty] | WAVE B | WAVE B | WAVE B(Half Day)

## Testers for wave B iteration 1
Succession |  | Available in SF proquire01T1
1 | camilla jacobson | Yes
2 | antje van willigen | Yes | Notes
3 | jayesh lindh | New | 1 | Performance is the week after and has no overlapping testing planned, so not including the tester names here.
4 | Malin AlexisNordin | New | 2 | RBP testers are not invited for iteration 1. Checking this. Will come back with the testers needed.
Learning
1 | femke bartels | New
2 | annika borlin | New
3 | rene tschierwitz | New
4 | michael neukirch | New
5 | elisabeth laitla | New
6 | rainer bitschi | New
7 | antje van willigen | Yes
8 | alan god | Yes
9 | patrick roscher | New
10 | Dam joost Van | New
Recruiting
1 | angelika Fuechtenhans | New
2 | jasmine vant hul | New
3 | bastiaan moll | New
4 | anna karin claeson | New
5 | jayesh lindh | New
6 | linn ljungman | New
7 | anja sergijenko | New
8 | lorraine melissen | New
9 | pi lindstroem | New
10 | antje van willigen | Yes
11 | linn rejstrom | New
12 | daniel t nilsson | New
RBP